## Project tasks
Project name | SIE - Copy |  | Resources
Project manager | Tanmay Kakade |  | Manager - M
Project start date | 2022-10-25 |  | Developer - D1, D2, D3
Project finish date | 2022-11-30 17:00 |  | Tester - T1, T2
Duration | 61 days
% complete | 0%
Exported on | 2022-10-26 01:54
Task number | Outline number | Name | Assigned to | Duration | Cost | Start | Finish | Depends on | % complete | Bucket | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels | Priority
1 | 1 | SIE |  | 61 days | 201572 | 2022-09-07 09:00 | 2022-11-30 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
2 | 1.1 | Iteration 1 |  | 9 days | 152825 | 2022-09-07 09:00 | 2022-09-19 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
3 | 1.1.1 | Requirements Gathering |  | 5 days | 4825 | 2022-09-07 09:00 | 2022-09-13 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
4 | 1.1.1.1 | Initial client meeting | M, D1, D2, D3 | 1 day | 831 | 2022-09-07 09:00 | 2022-09-07 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
5 | 1.1.1.2 | Team meeting | M, D1, D2, D3, T1, T2 | 1 day | 1166 | 2022-09-08 09:00 | 2022-09-08 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
6 | 1.1.1.3 | Team meeting with client | M, D1, D2, D3, T1, T2 | 1 day | 1166 | 2022-09-09 09:00 | 2022-09-09 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
7 | 1.1.1.4 | Final draft of requirements | M, D1, D2, D3 | 1 day | 831 | 2022-09-12 09:00 | 2022-09-12 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
8 | 1.1.1.5 | Approval from client | M, D1, D2, D3 | 1 day | 831 | 2022-09-13 09:00 | 2022-09-13 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
9 | 1.1.2 | System requirements |  | 4 days | 148000 | 2022-09-14 09:00 | 2022-09-19 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
10 | 1.1.2.1 | Hardware requirements | D1, D2, D3 | 2 days | 40000 | 2022-09-14 09:00 | 2022-09-15 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
11 | 1.1.2.2 | Software requirements | D1, D2, D3 | 2 days | 108000 | 2022-09-16 09:00 | 2022-09-19 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
12 | 1.2 | Iteration 2 |  | 10 days | 10655 | 2022-09-20 09:00 | 2022-10-03 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
13 | 1.2.1 | Design and Planning |  | 10 days | 10655 | 2022-09-20 09:00 | 2022-10-03 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
14 | 1.2.1.1 | Team meeting | M, D1, D2, D3, T1, T2 | 3 days | 3498 | 2022-09-20 09:00 | 2022-09-22 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
15 | 1.2.1.2 | Hardware and software cost estimation | M, D1, D2, D3, T1, T2 | 2 days | 2332 | 2022-09-23 09:00 | 2022-09-26 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
16 | 1.2.1.3 | Hardware and software setup plan | M, D1, D2, D3, T1, T2 | 2 days | 2332 | 2022-09-27 09:00 | 2022-09-28 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
17 | 1.2.1.4 | Architectural design | M, D1, D2, D3 | 3 days | 2493 | 2022-09-29 09:00 | 2022-10-03 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
18 | 1.3 | Iteration 3 |  | 2 days | 2332 | 2022-10-04 09:00 | 2022-10-05 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
19 | 1.3.1 | Hardware/software setup |  | 2 days | 2332 | 2022-10-04 09:00 | 2022-10-05 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
20 | 1.3.1.1 | Hardware setup | M, D1, D2, D3, T1, T2 | 1 day | 1166 | 2022-10-04 09:00 | 2022-10-04 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
21 | 1.3.1.2 | Software setup | M, D1, D2, D3, T1, T2 | 1 day | 1166 | 2022-10-05 09:00 | 2022-10-05 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
22 | 1.4 | Iteration 4 |  | 25 days | 20775 | 2022-10-06 09:00 | 2022-11-09 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
23 | 1.4.1 | Implementation/Coding | M, D1, D2, D3 | 25 days | 20775 | 2022-10-06 09:00 | 2022-11-09 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
24 | 1.5 | Iteration 5 |  | 5 days | 4327 | 2022-11-10 09:00 | 2022-11-16 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
25 | 1.5.1 | Integration Testing |  | 5 days | 4327 | 2022-11-10 09:00 | 2022-11-16 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
26 | 1.5.1.1 | Test plan | M, T1, T2 | 1 day | 665 | 2022-11-10 09:00 | 2022-11-10 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
27 | 1.5.1.2 | Test cases and Use cases | M, T1, T2 | 2 days | 1330 | 2022-11-11 09:00 | 2022-11-14 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
28 | 1.5.1.3 | Detect and Fix Errors | M, D1, D2, D3, T1, T2 | 2 days | 2332 | 2022-11-15 09:00 | 2022-11-16 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
29 | 1.6 | Iteration 6 |  | 8 days | 8326 | 2022-11-17 09:00 | 2022-11-28 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
30 | 1.6.1 | Unit Testing |  | 8 days | 8326 | 2022-11-17 09:00 | 2022-11-28 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
31 | 1.6.1.1 | Coverage testing | M, T1, T2 | 2 days | 1330 | 2022-11-17 09:00 | 2022-11-18 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
32 | 1.6.1.2 | Bugs Detection | M, D1, D2, D3, T1, T2 | 3 days | 3498 | 2022-11-21 09:00 | 2022-11-23 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
33 | 1.6.1.3 | Errors Fixing | M, D1, D2, D3, T1, T2 | 3 days | 3498 | 2022-11-24 09:00 | 2022-11-28 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium
34 | 1.7 | Iteration 7 |  | 2 days | 2332 | 2022-11-29 09:00 | 2022-11-30 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
35 | 1.7.1 | Product Delivery | M, D1, D2, D3, T1, T2 | 2 days | 2332 | 2022-11-29 09:00 | 2022-11-30 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium